## Dashboard
Reader Runtime Solidification - Sprint Dashboard
Total Sprints | Completed | Remaining | % Complete | Total LOE | LOE Completed | LOE Remaining
35 | 35 | 3 | 92.11% | 125 | 90 | 35
Queue Source of Truth | docs/governance/sprint-queue.xlsx
Queue Depth | 5 | Full Specs | 5 | Stubs | 0
NARRATE-HEARD-CURSOR-1 | NARRATE-APPLYRATECHANGE-COLLAPSE-1 | Next Phase | Reader Runtime Solidification - Stage 2 Adapter Isolation
Dashboard Updated | 2026-07-02

## Catalog
Seq | Sprint Code | Title | Phase | Stage | LOE | Dependencies | Implementation Status | Written Status | Description | Branch | Date Started | Date Completed | Close-Out File | Notes
| KOKORO-DEEPEN-1 | Kokoro Readiness & Preflight | TTS Architecture | Deepening | 3 |  | Complete | Full spec | Kokoro readiness and preflight checks |  |  | 2026-05-11
| KOKORO-DEEPEN-2 | Natural Chunk Highlight | TTS Architecture | Deepening | 3 |  | Complete | Full spec | Natural chunk highlighting for Kokoro TTS |  |  | 2026-05-11
| KOKORO-DEEPEN-3 | Voice Mixing Feasibility | TTS Architecture | Deepening | 1 |  | Complete | Full spec | Voice mixing feasibility study |  |  | 2026-05-11
| TTS-REGISTRY-1 | Provider Capability Registry | TTS Architecture | Foundation | 3 |  | Complete | Full spec | Provider capability truth in ttsProviderRegistry |  |  | 2026-05-12 | ROADMAP_ARCHIVE_2026-05-14.md
| TTS-NORMALIZE-1 | Segment Normalizer | TTS Architecture | Foundation | 3 |  | Complete | Full spec | English-first spoken-text normalization |  |  | 2026-05-13 | ROADMAP_ARCHIVE_2026-05-14.md
| TTS-CACHE-TIMING-1 | Cache Identity & Timing Sidecars | TTS Architecture | Foundation | 3 |  | Complete | Full spec | Schema-versioned v2 cache identities and atomic timing sidecars |  |  | 2026-05-13 | ROADMAP_ARCHIVE_2026-05-14.md
| TTS-SYNC-1 | Highlight Sync Controller | TTS Architecture | Sync & Diagnostics | 8 | TTS-CACHE-TIMING-1 | Complete | Full spec | Centralized narration highlight sync policy | sprint/tts-sync-1-highlight-controller |  | 2026-05-15 | docs/Close-Outs/CloseOut.TTS-SYNC-1.2026-05-15.md
| TTS-DIAG-1 | Narration Diagnostics Bundle | TTS Architecture | Sync & Diagnostics | 3 | TTS-SYNC-1 | Complete | Full spec | Provider-neutral diagnostics bundle | sprint/tts-diag-1-diagnostics-bundle |  | 2026-05-15 | docs/Close-Outs/CloseOut.TTS-DIAG-1.2026-05-15.md
| ENGINE-DORMANCY-1 | Disable MOSS-Nano & Pocket TTS | TTS Architecture | Consolidation | 1 | None | Complete | Full spec | Disable dormant sidecar engines |  |  | 2026-05-16 | docs/governance/close-outs/CloseOut.ENGINE-DORMANCY-1.2026-05-16.md | Dormant at settings/IPC; code preserved; Nano probes opt-in.
| TTS-INTEGRATE-1 | Integrate Sync & Diagnostics | TTS Architecture | Consolidation | 2 | ENGINE-DORMANCY-1 | Complete | Full spec | Merge sync and diagnostics branches to main |  |  |  |  | Dispatch-ready; dormancy gate complete.
| TTS-CACHE-HARDEN-1 | Cache/Pipeline Hardening | TTS Architecture | Consolidation | 2 | TTS-INTEGRATE-1 | Complete | Full spec | Cache-hit timing parity, type harmonization, IPC validation |  |  |  |  | Findings-driven: impl review A8 + lit review §4.6
| TTS-EVENT-SYNC-1 | Event-Driven Word Sync | TTS Architecture | Stage 2: Event-Driven Sync | 3 | TTS-CACHE-HARDEN-1 (completed 2026-05-16) | Complete | Full spec | Event-driven word sync from research | sprint/tts-event-sync-1-word-boundary-sync |  | 2026-05-16 | docs/governance/close-outs/CloseOut.TTS-EVENT-SYNC-1.2026-05-16.md | Research: readest + RealtimeTTS + sioyek; landed a71df02 via 2c946ad; governance commit 800c9e2
| NORMALIZER-ENRICH-1 | Normalizer Gap Fill | TTS Architecture | Stage 2: Normalizer Enrichment | 3 | TTS-EVENT-SYNC-1 | Complete | Full spec | Fill normalizer gaps from abogen research | sprint/normalizer-enrich-1-kokoro-text-normalization |  | 2026-05-17 | docs/governance/close-outs/CloseOut.NORMALIZER-ENRICH-1.2026-05-17.md | Research: abogen. Landed de5b441, merged dcf8a7d, governance closeout 2c7ada8.
| TTS-RENDER-MAP-1 | Word Position Index | TTS Architecture | Stage 2: Word Position Index | 3 | NORMALIZER-ENRICH-1 | Complete | Full spec | Sioyek-inspired word position index | sprint/tts-render-map-1-word-position-index | 2026-05-17 | 2026-05-17 | docs/governance/close-outs/CloseOut.TTS-RENDER-MAP-1.2026-05-17.md | Research: sioyek. Landed 2eabf36, merged 8545895.
| TTS-PIPELINE-1 | Pipeline Integration Tests | TTS Architecture | Stage 3: Pipeline Truth | 1 | TTS-RENDER-MAP-1 | Complete | Full spec | End-to-end pipeline integration tests | sprint/tts-pipeline-1-integration-test | 2026-05-17 | 2026-05-17 | docs/governance/close-outs/CloseOut.TTS-PIPELINE-1.2026-05-17.md | Pipeline identity/integration coverage. Landed 022d161, merged 994f218.
| TTS-ARCH-DOC-1 | Architecture Decisions Doc | TTS Architecture | Stage 4: Governance | 1 | All above | Complete | Full spec | Architecture decision records for TTS | sprint/tts-arch-doc-1-architecture-decisions | 2026-05-17 | 2026-05-17 | docs/governance/close-outs/CloseOut.TTS-ARCH-DOC-1.2026-05-17.md | Architecture decision record. Landed 66a73b1, merged 65629bc.
| TEST-HARNESS-1 | Test Harness Stability | TTS Architecture |  | 2 |  | Dissolved |  | Test harness stability work |  |  |  |  | Dissolved 2026-05-15 — Nano probes irrelevant
| TTS-CANARY-1 | Engine Readiness Probes | TTS Architecture |  | 1 |  | Dissolved |  | Engine readiness probe system |  |  |  |  | Dissolved 2026-05-15 — sidecar engines dormant
| TTS-REGISTRY-DISPATCH-1 | Registry-Driven Dispatch | TTS Architecture |  | 3 |  | Dissolved |  | Registry-driven engine dispatch |  |  |  |  | Dissolved 2026-05-15 — single active engine
| KOKORO-EXPORT-1 | Long-Form Audio Export | TTS Architecture |  | 8 | TTS-ARCH-DOC-1 | Blocked | Full spec | Long-form audio export from Kokoro |  |  |  |  | Deferred to post-TTS-Architecture phase. Worktree preserved at .worktrees/kokoro-export-1 (37 tests pass).
| NARR-MEDIA-1 | MediaSession Controls | Narration UX | Post-Architecture Polish | 1 | TTS-ARCH-DOC-1 | Dissolved | Full spec | OS media transport controls for active narration |  |  |  |  | Dissolved — duplicate of completed NARR-MEDIA-1 in TTS Quality phase
| NARR-PAUSE-STATE-1 | Named Pause State Machine | Narration UX | Post-Architecture Polish | 2 | NARR-MEDIA-1 | Dissolved | Full spec | Reason-aware pause and resume state transitions |  |  |  |  | Superseded by new TTS Quality + Reading Exp v2 conveyor (2026-05-17)
| NARR-MEDIA-1 | MediaSession Integration | TTS Quality + Reading Exp v2 | 1a | S | None | Complete | Full Spec | OS media controls via Electron MediaSession API | sprint/narr-media-1-mediasession |  | 2026-05-17 | CloseOut.NARR-MEDIA-1.2026-05-17.md
| NARR-PAUSE-1 | Named-Pause State Machine | TTS Quality + Reading Exp v2 | 1a | M | None | Completed | Full Spec | PauseReason discriminant for smarter resume behavior | sprint/narr-pause-1-named-pause |  | 2026-05-18 | CloseOut.NARR-PAUSE-1.2026-05-18.md
| TTS-PARITY-1 | Cache/Progress/Resume Parity Hardening | TTS Quality + Reading Exp v2 | 1a | S | NARR-PAUSE-1 | Completed | Full Spec | Fix cache silence parity, trusted progress lag, resume backpressure | sprint/tts-parity-1 |  | 2026-05-18 | CloseOut.TTS-PARITY-1.2026-05-18.md | OutsideAudit.9 hardening gate. Three defects, three tests.
| NARR-CURSOR-2 | Silence-Aware Cursor Hold | TTS Quality + Reading Exp v2 | 1a | S | NARR-PAUSE-1, TTS-PARITY-1, NARR-SPOKEN-1 | Completed | Full Spec | Freeze cursor during inter-word silence using real endTime timestamps | sprint/narr-cursor-2-silence-hold |  | 2026-05-18 | CloseOut.NARR-CURSOR-2.2026-05-18.md
| TTS-EVAL-3 | Quality Evaluation + CI Gate | TTS Quality + Reading Exp v2 | 1b | M | None | Completed | Full Spec | Extend eval harness with quality scoring dimensions and CI gate config | sprint/tts-eval-3-quality-ci-gate |  | 2026-05-18 | CloseOut.TTS-EVAL-3.2026-05-18.md
| NARR-SPOKEN-1 | Spoken/Display Word Separation | TTS Quality + Reading Exp v2 | 1a | M | TTS-PARITY-1 | Completed | Full Spec | Filter punctuation-only tokens from phoneme alignment input | sprint/narr-spoken-1 |  | 2026-05-18 | CloseOut.NARR-SPOKEN-1.2026-05-18.md
| BASELINE-SYNC-1 | Commit Phase 0 + Governance Sweep Baseline | Reader Runtime Solidification | 0 | M | READER-MODE-ISOLATION-1 Phase 0; GOVERNANCE-SWEEP | Completed | Full Spec | Review, stage, verify, and commit Phase 0 plus governance sweep baseline | main/current dirty baseline sync |  | 2026-05-22 | CloseOut.BASELINE-SYNC-1.2026-05-22.md | Completed in three pushed commits: reader anchors, governance sweep, roadmap queue resequence.
| TEST-GREEN-1 | Broad Suite Failure Triage | Reader Runtime Solidification | 1 | M | BASELINE-SYNC-1 | Completed | Full Spec | Reproduce and classify broad-suite failures before CI gating | sprint/test-green-1-broad-suite-triage |  | 2026-05-22 | CloseOut.TEST-GREEN-1.2026-05-22.md | Completed at 172cffb; 12 failures classified/resolved, 3 environmental flakes documented.
| READER-PERSISTENT-ANCHOR-STEP3-REPAIR | Persistent Anchor Step 3.6 Content-Contiguous Synthesis (NARRATE-CURSOR-SYNC-5, Bug 2) | Reader Runtime Solidification | 1 | L | Step 3.5 manual QA: S13 split -> Bug2 content omission (this); Bug1 visual lead deferred post-ISO | Complete | Full Spec | Fix content omission: seed automatic chunk continuation from produced-end (nextGenWordIndexRef), not lastConfirmedAudioWordRef (cursor twin); hard-click still re-anchors. Add schedule-vs-wallclock log. Gate: no words omitted by ear in The Raven. See ROADMAP Step 3.6. | hotfix/reader-persistent-anchor | 2026-05-24 | 2026-05-24 | docs/governance/close-outs/CloseOut.READER-PERSISTENT-ANCHOR-STEP3.6.2026-05-24.md | Repair lane closed by explicit disposition; S1/S4/S8/S12/S18 fixed, S5 accepted partial, S9 deferred, S13 moved to post-isolation NARRATE-CLOSED-LOOP-CURSOR.
| READER-ISO-1A | Adapter Contracts + Current Word Anchor Service | Reader Runtime Solidification | 2 | M | READER-PERSISTENT-ANCHOR-STEP3-REPAIR; TEST-GREEN-1 | Complete | Full Spec | Add adapter contracts and tested shared current-word anchor service | sprint/reader-iso-1a-adapter-anchor-contracts | 2026-05-24 | 2026-05-24 | docs/governance/close-outs/CloseOut.READER-ISO-1A.2026-05-24.md | Completed and merged to main at 32f4543; behavior-preserving adapter contract and anchor service sprint.
| READER-ISO-1B | Orchestrator Shell + Mode Selection Semantics | Reader Runtime Solidification | 2 | L | READER-ISO-1A | Complete | Full Spec | Extract mode orchestrator shell while preserving exact-start and no-auto-start semantics | sprint/reader-iso-1b-orchestrator-shell | 2026-05-25 | 2026-05-25 | docs/governance/close-outs/CloseOut.READER-ISO-1B.2026-05-25.md | Completed and merged to main at 1f4a75a; behavior-preserving orchestrator shell extraction.
| READER-ISO-1C | Focus Adapter + Passive Surface Contract Start | Reader Runtime Solidification | 2 | M | READER-ISO-1B | Complete | Full Spec | Move Focus behind adapter and begin passive surface command typing | sprint/reader-iso-1c-focus-adapter | 2026-05-26 | 2026-05-26 | docs/governance/close-outs/CloseOut.READER-ISO-1C.2026-05-26.md | Completed and merged to main at 634bac2; first concrete Focus adapter plus passive SurfaceCommand types.
| READER-ISO-1D | Flow Adapter + Section Handoff Restart Ownership | Reader Runtime Solidification | 2 | L | READER-ISO-1C; persistent-anchor repair lane closed by explicit disposition; Flow S9 lazy-follow deferred | Complete | Full Spec | Move Flow lifecycle and FlowScrollEngine ownership behind Flow adapter | sprint/reader-iso-1d-flow-adapter |  | 2026-05-26 | docs/governance/close-outs/CloseOut.READER-ISO-1D.2026-05-26.md | Flow owns section-handoff restart; no Narrate truth-sync changes.
| READER-ISO-1E | Narrate Adapter + Audio Truth-Sync Ownership | Reader Runtime Solidification | 2 | L | READER-ISO-1D | Complete | Full Spec | Move Narrate lifecycle behind audio truth-sync owned adapter |  |  | 2026-05-27 | docs/governance/close-outs/CloseOut.READER-ISO-1E.2026-05-27.md | Narrate starts at exact selected/current word and never follows Flow engine.
| GOV-HUMAN-REVIEW-1 | Deferred Governance Review Items | Reader Runtime Solidification | Governance | S | BASELINE-SYNC-1 | Complete | Full Spec | Resolve deferred governance-sweep human-review items |  |  | 2026-05-27 | docs/governance/close-outs/CloseOut.GOV-HUMAN-REVIEW-1.2026-05-27.md | Docs-only. Doc-keeper agent renamed Herodotus -> MarcusAurelius across canonical surfaces; Hercules.md -> hercules.md; 8 close-outs archived; rosters reconciled; governance-sweep-spec archived. Merge handed off to user per git-handoff rule.
| TTS-QUAL-CI-1 | CI Regression Gate Wiring | Reader Runtime Solidification | Active Conveyor Belt | S | TEST-GREEN-1; TTS-EVAL-3 | Completed | Full Spec | Wire TTS quality gates into CI after suite health and reader runtime are stable | sprint/tts-qual-ci-1 | 2026-05-28 | 2026-05-28 | CloseOut.TTS-QUAL-CI-1.2026-05-28.md | Deferred until broad-suite health is clean or formally classified.
4 | UX-POLISH-1 | Space-bar resumes last-used reading mode | Reader Runtime Solidification | Active Conveyor Belt | XS | Reader runtime stable | Queued | Full Spec | Rescoped 2026-07-02: 3 of 4 original UX-POLISH features already shipped (3-line cards, New-dot+auto-clear, Ctrl+K palette). Remaining: page-mode Space enters settings.lastReadingMode. | sprint/ux-polish-1 |  |  |  | Deferred until reader-mode runtime controls stop churning.
| NARRATE-CLOSED-LOOP-CURSOR | Narrate Closed-Loop Cursor + Content Continuity (real audio position as single truth) | Reader Runtime Solidification | Active Conveyor Belt | L | READER-ISO-1E (Narrate adapter) complete | Dissolved | Full Spec | Make currently-playing audio source's real word position the SINGLE source of truth for cursor + re-entry seeding; retire ahead-of-heard refs; bound prefetch window. | sprint/narrate-closed-loop-cursor |  | 2026-05-29 | See Disposition of Superseded Branches in ROADMAP.md; branch preserved at sprint/narrate-closed-loop-cursor commit 0f1b2c8 | Superseded 2026-05-29 by NARRATE-DUAL-SOURCE-DIAG-1 + INTENT-CURSOR-1 + PAUSE-RESUME-UNIFY-1 + APPLYRATECHANGE-COLLAPSE-1 + SUBSCRIBER-CURSOR-1 after live-QA A4 FAIL + ULTRATHINK identified dual-source root cause requiring 5-sprint completion of the unification
| EXT-PAIR-1 | Chrome Extension Pairing Auth Timeout Repair | Reader Runtime Solidification | Active Conveyor Belt | XS |  | Completed | Full Spec | Split WS_AUTH_TIMEOUT_MS into a generous pairing window (5 min) for first-time human pair and the existing tight 5s window for stored-token re-auth. Closes BUG-183. | sprint/ext-pair-1 | 2026-05-29 | 2026-05-29 | CloseOut.EXT-PAIR-1.2026-05-29.md | Hotfix for BUG-183 (filed 2026-05-28). Aristotle-gated. Parallel-safe with TTS-QUAL-CI-1 + SINGLE-INSTANCE-LOCK-1.
| SINGLE-INSTANCE-LOCK-1 | Electron Main-Process Single-Instance Gate | Reader Runtime Solidification | Completed | XS |  | Completed | Full Spec | Add app.requestSingleInstanceLock() + second-instance handler to focus existing window instead of spawning duplicate BrowserWindow. ~5 LOC. Closes F1 from discovery sweep. | sprint/single-instance-lock-1 | 2026-05-29 | 2026-05-29 | CloseOut.SINGLE-INSTANCE-LOCK-1.2026-05-29.md | XS effort. Manual smoke PASS (launch twice -> one window, existing window focuses/restores). Parallel-safe with everything in buffer (Lane D, main-process only).
| THEME-SYNC-1 | Settings Theme Propagation + Vite Circular Chunk Repair | Reader Runtime Solidification | Completed | S |  | Completed | Full Spec | Resolve settings↔tts circular chunk warning and audit theme-context subscription across Settings sub-pages. Closes BUG-182. | sprint/theme-sync-1 | 2026-05-29 | 2026-05-29 | CloseOut.THEME-SYNC-1.2026-05-29.md | Hotfix for BUG-182. Build clean; live smoke PASS on v1.75.1 dev build with E-Ink Display Mode OFF. New BUG-184 filed for einkMode panel transparency.
5 | HYG-XLSX-DASHBOARD-RESTORE | Restore sprint-queue.xlsx Dashboard formulas + openpyxl quarantine | Reader Runtime Solidification | Active Conveyor Belt | S |  | Queued | Full Spec | Restore Dashboard KPIs as live Excel formulas + normalize Catalog vocab/LOE + recalc.py Dashboard guardrail + SPREADSHEET_CONVENTIONS.md. Dashboard confirmed inert (0 formula cells). | sprint/hyg-xlsx-dashboard-restore |  |  |  | Created during TTS-QUAL-CI-1 close-out 2026-05-28. Lane E governance tooling. Parallel-safe with all other queued sprints.
| NARRATE-DUAL-SOURCE-DIAG-1 | Validate Dual-Source Diagnosis via Instrumented Gate Replay | Reader Runtime Solidification | Narration Dual-Source Unification | XS | NARRATE-CLOSED-LOOP-CURSOR dissolved | Completed | Full Spec | 1-day investigation: instrument every audio-decision read in useNarration.ts, re-run live-QA A1/A4/A5, produce verdict report confirming/refuting dual-source diagnosis from 2026-05-29 ULTRATHINK | sprint/narrate-dual-source-diag-1 |  | 2026-05-30 | docs/governance/close-outs/CloseOut.NARRATE-DUAL-SOURCE-DIAG-1.2026-05-30.md | Gating sprint for positions 2-5. Per SRL-072: do not iterate on ahead-of-heard refs without first verifying their role. Logs gated by localStorage.BLURBY_DUAL_SOURCE_DIAG="1". ¦ Verdict YELLOW: A4=reader-layer resumeAnchor (dual-source race REFUTED), A5=wrong rate seed.
| NARRATE-INTENT-CURSOR-1 | Intent Cursor with SET to ACTIVE to CONSUMED to CLEARED Lifecycle | Reader Runtime Solidification | Narration Dual-Source Unification | S | NARRATE-DUAL-SOURCE-DIAG-1 (verdict CONFIRMED or PARTIAL) | Completed | Full Spec | Introduce intentCursorRef as user-intent half of Evan's two-cursor model; retire nextKokoroExactStartRef (the secret cursor); resyncToCursor becomes thin wrapper that sets intent + triggers restartGeneration if playing | sprint/narrate-intent-cursor-1 |  | 2026-05-31 | CloseOut.NARRATE-INTENT-CURSOR-1.2026-05-31.md | PARTIAL: A1 PASS, A4 FAIL 0-of-3. Consume lifecycle landed; reactive not preventive. PAUSE-RESUME-UNIFY-1 completes.
| NARRATE-PAUSE-RESUME-UNIFY-1 | Fix A4 via resumeTargetRef Capture-at-Pause + Unified Resume Seed | Reader Runtime Solidification | Narration Dual-Source Unification | S | NARRATE-INTENT-CURSOR-1 (provides getNextChunkSeed helper) | Completed | Full Spec | Introduce resumeTargetRef; pause() captures heardFloor BEFORE strategy clears scheduler sources; resume() reads from priority chain intent ?? resumeTarget ?? subscriber. Fixes A4 (play->pause->play resets to book start). | sprint/narrate-pause-resume-unify-1 |  | 2026-05-31 | docs/governance/close-outs/CloseOut.NARRATE-PAUSE-RESUME-UNIFY-1.2026-05-31.md | Source merged at db2d1bc; anchor-correctness follow-up merged at 1299808. Live A4 retest still recommended before user-facing gate is declared closed.
2 | NARRATE-APPLYRATECHANGE-COLLAPSE-1 | Collapse 14 Reseed Paths + Delete Dormant-Engine Code (Kokoro-Only) | Reader Runtime Solidification | Narration Dual-Source Unification | M | NARRATE-PAUSE-RESUME-UNIFY-1 (restartGeneration helper to extend) | Queued | Full Spec | Collapse 14 speakNextChunk paths in applyRateChange (lines 1722-1871) into single restartGeneration(reason) helper; delete Web/Qwen/Pocket/Nano reseed branches per Kokoro-only design constraint; fold applyVoiceChange into same helper. Fixes A5 (rate-change skip). | sprint/narrate-applyratechange-collapse-1 |  |  |  | Also owns: A5 1.4x-bucket overlap buffer-flush (cancel prior-tempo queued sources on rate-INCREASE; only 1.4x jumbles, 1.2/1.3 clean) + unblocks SUBSCRIBER-CURSOR-1 reducer-removal (remove last cursorWordIndex audio readers).
3 | NARRATE-SUBSCRIBER-CURSOR-1 | Retire WORD_ADVANCE Reducer Action; Visual Highlight via Direct Callback | Reader Runtime Solidification | Narration Dual-Source Unification | M | NARRATE-CURSOR-TRACKING-DIAG-1; NARRATE-APPLYRATECHANGE-COLLAPSE-1 | Blocked | Full Spec | If NARRATE-CURSOR-TRACKING-DIAG-1 confirms the subscriber/direct-callback model, rename lastConfirmedAudioWordRef -> subscriberCursorRef, remove cursorWordIndex from React reducer state, remove WORD_ADVANCE action, and wire visual/view follow via the verdict-approved live target. | sprint/narrate-subscriber-cursor-1 | 2026-05-31 |  |  | GATED on NARRATE-HEARD-CURSOR-1 live-QA (2026-06-01 restructuring). Heavy WORD_ADVANCE/reducer removal dispatches ONLY if HEARD-CURSOR-1 verdict is PARTIAL (residual React-batching lead). PASS => unnecessary (dissolve/defer). Wave A enumeration folded into HEARD-CURSOR-1.
| NARRATE-A5-RATE-RESEED-1 | Rate-Change Reseed from Heard Position | Reader Runtime Solidification | Active Conveyor Belt | S | NARRATE-DUAL-SOURCE-DIAG-1 | Completed | Full Spec | Reseed applyRateChange Kokoro bucket-change from heardFloor, not nextGenWordIndexRef (A5 fix) | sprint/narrate-a5-rate-reseed-1 |  | 2026-05-31 | docs/studies/investigations/NARRATE-A5-RATE-RESEED-liveqa-gate-report.md | Position fix merged 145c385; residual 1.4x-bucket overlap -> APPLYRATECHANGE-COLLAPSE-1. No formal CloseOut authored (interim evidence: live-QA gate report). Reconciled 2026-07-02.
| NARRATE-CURSOR-TRACKING-DIAG-1 | Narrate Cursor Tracking Diagnostic | Reader Runtime Solidification | Active Conveyor Belt | S | NARRATE-PAUSE-RESUME-UNIFY-1; revert fcea6a8 | Completed | Full Spec | Instrument cursor, heard-floor, anchor, Foliate, and Flow follow signals to prove which source should drive visible cursor and view-follow before another fix. | sprint/narrate-cursor-tracking-diag-1 | 2026-05-31 | 2026-05-31 | docs/governance/close-outs/CloseOut.NARRATE-CURSOR-TRACKING-DIAG-1.2026-05-31.md | Live-QA trace 2026-05-31 (Meditations, DIAG on/reverted). Hypothesis REFUTED: schedulerActiveWord==heardFloor lead the heard voice; wordIndex (visible cursor) closest but still leads & drifts; nextGenWordIndex is pre-fetch frontier; resumeTarget/subscriberCursor no-data. SUBSCRIBER-CURSOR-1 amended -> publish lag-compensated heard cursor. See investigations/NARRATE-CURSOR-TRACKING-DIAG-1.md.
1 | NARRATE-HEARD-CURSOR-1 | Drive Highlight + Reading-Window from One Tunable Lag-Compensated Heard Cursor | Reader Runtime Solidification | Narration Dual-Source Unification | S | NARRATE-CURSOR-TRACKING-DIAG-1 (verdict); NARRATE-PAUSE-RESUME-UNIFY-1 | Queued | Full Spec | Route both the visible highlight and FlowScrollEngine.followWord through ONE lag-compensated heard cursor (getAudioProgress / heard-floor clamp); extract tunable TTS_VISUAL_CURSOR_LAG_MS; tune by ear. No reducer/WORD_ADVANCE change. Live-QA verdict gates SUBSCRIBER-CURSOR-1. | sprint/narrate-heard-cursor-1 |  |  |  | 2026-06-01 ULTRATHINK probe-first restructuring (NARRATE-CURSOR-WINDOW-SYNC.md). The cheap reversible test of the cursor/window fix. PASS closes the desync line; PARTIAL dispatches SUBSCRIBER-CURSOR-1; FAIL re-opens investigation.